## Sheet1
Activity | Weight | Resources |  |  | Sum | depends | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Days | Type 1 | Type 2 | Type 3
A | 4 | 2st | - | - | 2 | bar: 1 to 4
B | 5 | 1st | 2st | 2st | 5 | bar: 5 to 9
C | 2 | - | 2st | 3st | 5 | bar: 11 to 12
D | 6 | 2st | 1st | - | 3 | bar: 5 to 10
E | 3 | 1st | 1st | 1st | 3 | bar: 11 to 13
F | 4 | - | - | 2st | 2 | bar: 11 to 14
G | 8 | 1st | 3st | 2st | 6 | bar: 13 to 20
H | 5 | 1st | 2st | 1st | 4 | bar: 15 to 19
I | 2 | 1st | 1st | - | 2 | bar: 21 to 22
[6 empty] | Resources / Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Total
11 | bar: 13
10 | bar: 11 to 13; 15 to 19
9 | bar: 11 to 13; 15 to 19
8 | bar: 5 to 9; 11 to 19
7 | bar: 5 to 9; 11 to 19
6 | bar: 5 to 9; 11 to 20
5 | bar: 5 to 9; 11 to 20
4 | bar: 5 to 9; 11 to 20
3 | bar: 5 to 20
2
1
11 resources are planned at the same time
Day 13 is the busiest working day in the project
Activity | Weight | Critical line
A | 3 | A->B = 20
B | 3 | B->E = 17
C | 4 | C->G = 12
D | 2 | D->E = 16
E | 7 | E->H = 14
F | 5 | F->I = 10
G | 6 | 8
H | 5 | 7
I | 3 | 5
J | 2 | 2

## Sheet3
Activity | Dependent | Duration hours (normal) | Shortest time the activity can be performed in | Cost (normal) | Cost per hour to shorten the time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
A | - | 14 | 14 | 14500kr | 1750kr
B | A | 16 | 14 | 17000kr | 1750kr
C | B | 8 | 8 | 8500kr | 1750kr
D | A | 4 | 4 | 4000kr | 1750kr
E | D | 18 | 16 | 19000kr | 1750kr
F | C | 36 | 16 | 38000kr | 1200kr
G | C | 20 | 16 | 22000kr | 1400kr
H | E | 14 | 8 | 15000kr | 1750kr
I | F | 14 | 6 | 15000kr | 1400kr
J | G, H | 20 | 12 | 21000kr | 1200kr
K | I, J | 80 | 70 | 85000kr | 1200kr
L | K | 20 | 18 | 21000kr | 5500kr
M | L | 20 | 16 | 21000kr | 5500kr
N | K | 5 | 5 | 5500kr | 5500kr
O | K | 8 | 3 | 8500kr | 5500kr
P | N, O | 16 | 10 | 15000kr | 5500kr
Q | M, P | 2 | 2 | 2000kr | 1200kr
Sum |  | 315 |  | 332000kr